## Open item list SFM level 3 (hidden)
|  |  |  | Open Item List / Action Plan Sheet | [6 empty] | Status Legend:
[11 empty] | ○ | <25% umgesetzt
Subject: |  |  | Gap analysis |  |  |  |  | Date : |  | 2017-08-17 | ◔ | 25% umgesetzt
Editor: |  |  | CC/SI | [7 empty] | ◑ | 50% umgesetzt
[6 empty] | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[11 empty] | ● | erledigt
Sr. No. | entered on: | Stn name | assigned by: | topic (Issue) | root cause (base for action) | to do / action | responsible: | due on: | status | comment:
1. | 17.08.2017 |  |  | Material delay from store 230 minute ( not found issue) | Casual reduced. Load distribution for material req. is not balanced. | Review the load distribution of req. add line feeding people. | Milind | 19.08.2017 | ○
|  |  |  | Material shortage in visco material & VW line. | Planning issue from PPC. | Planning & produce to signoff the material availability for next day production. | Milind | 18.08.2017 | ○
|  |  |  | Helium cylinder shortage/ delay. X-over motor shortage. | Communication gap between store & production team. | We will take meeting internal with concerned person. | Milind | 18.08.2017 | ○
2 | 18.08.2017 |  |  | material shortage MAN, HEXA, P9218, Volvo, AH. |  |  |  |  | ○
|  |  |  | Material delay from the store & not found. HVAC, visco, all wiring. |  |  |  |  | ○
|  |  |  | Eagle manifold quality issue. |  | SQA team will make correction by visiting supplier. |  |  | ○
3 | 19.08.2017 |  |  | Material delay from store HVAC & Visco (319+40)=359 mins | Casual reduced in store. | Casual word load calculated. Need to increase manpower. Today it will take with Mr. Tribhuwan sir. | Yoghesh Phadtare/ Milind | 24.08.2017 | ○
|  |  |  | Material shortage. X1- CC848001 -impeller Y1-EV781001, GC949001, KH444001 | CC848001 - Mould blower current stock can be used till 28th & mould should get ready. | Supplier quality working on that. We will close this topic tomorrow. | Ganesh/ Millind | 23.08.2017 | ○
|  |  |  | Eagle manifold quality issue. |  |  |  |  | ○
4 | 21.08.2017 |  |  | Material delay from store HVAC & Visco. |  |  |  |  | ○
|  |  |  | Trolley shortage(Y1, VW, Compact, Hexa & X1) |  |  |  |  | ○
|  |  |  | M300 manifold/ slot undersize. CB1 - Fin cutting issue. U301 CAC trolley volvo heater box. J92 Evap. |  |  |  |  | ○
6 | 22.08.2017 |  |  | Material shortage. Hexa,MPV, Y1, X104, M300 condenser, radiator. | X104 rejected due to wrong sealing pasted by supplier. Hexa sealing not found.MPV & Y1 delivery failure. | Ok parts come from suppplier. One DOH maintain at supplier end. | Jagjivan | 22.08.2017 | ○
|  |  |  | Material delay from store.( VW, X1, Compact, Evap. Coil) | Manpower shortage for store operation.(MP cut down). Flow for helium is not defined. | Discussion with HR head on casual approval. Kaizen to improve storage flow of cylinder in inward. | Kashyap | 22.08.2017 | ○
|  |  |  | Evap. Fin height variation - 40 mm |  |  |  |  | ○
7 | 23.08.2017 |  |  | Condenser CB1 net transfer problem. |  |  |  |  | ○
|  |  |  | Helium cylinder shortage(EC/ AH) |  |  |  |  | ○
|  |  |  | Material shortage. Comapct & CP - 230 mins Material delay from store - 534 mins(HVAC & Visco). |  | We will ensure in advance. | Milind |  | ○
8 | 29.08.2017 |  |  | Material delay from store HVAC & Visco. |  | Manpower addition to line feeding trying to get approval from HR. Hopeful for today | Kashyap | 30.08.2017 | ○
|  |  |  | Material shortage. HAVC- MAN,M&M, VW. Visco- Fan shortage. |  | For Visco adding box & arranging advance from next two days. | Ganesh / Milind | 01.09.2017 | ○
9 | [8 empty] | ○
○
○
10 | [8 empty] | ○
○
○
11 | [8 empty] | ○
○
○
12 | [8 empty] | ○
○
○
13 | [8 empty] | ○
○
○
14 | [8 empty] | ○
○
○
15 | [8 empty] | ○
○
○
16 | [8 empty] | ○
17 | [8 empty] | ○
18 | [8 empty] | ○
19 | [8 empty] | ○
20 | [8 empty] | ○
21 | [8 empty] | ○
22 | [8 empty] | ○
23 | [8 empty] | ○
24 | [8 empty] | ○
25 | [8 empty] | ○
26 | [8 empty] | ○
27 | [8 empty] | ○
28 | [8 empty] | ○
29 | [8 empty] | ○
30 | [8 empty] | ○
31 | [8 empty] | ○
32 | [8 empty] | ○
33 | [8 empty] | ○
34 | [8 empty] | ○
○

## List Of Projects - Aug 2017 (hidden)
|  |  | Level 3 Meeting - List Of Projects |  |  |  |  | Status Legend:
[8 empty] | ○ | <25% umgesetzt
Subject: |  | CIP projects for the issues of Aug 2017 |  |  | Date : |  | 2017-08-02 | ◔ | 25% umgesetzt
Editor: |  | Valmik S | [5 empty] | ◑ | 50% umgesetzt
|  |  | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[8 empty] | ● | erledigt
Sr. No. | Entered on: | Assigned by: | Project Title | Responsible: | Due on: | Status | Comment:
1 | 31.08.2017 | Valmik S | Eliminate the material delay from issue | Kashyap B |  | ○
2 | 31.08.2017 | Valmik S | Strategy to develop alternate supplier for Visco Shaft supplies | Vijay S |  | ○
3 | 31.08.2017 | Valmik S | Stategy to develop alternate supplier for Visco Fan supplies | Vijay S |  | ○
4 | 31.08.2017 | RV | Streamlining of Healium cylinder inwarding process and storage arrangement to avoid production line stoppage | Kashyap B |  | ○
5 | 31.08.2017 | RV | Statergy to develop alternate supplier for Hexa Radiator motor | Vijay S |  | ○
6 | 31.08.2017 | RV | Streamlining the bin replinishing process of VW HVAC impeller | Ganesh J / Milind M |  | ○
7 | 31.08.2017 | RV | Improving the MTBF of Condensor Core builder by analysing the downtime and intiating the actions | Abhay B |  | ○
8 | 31.08.2017 | RV | Improving Condenser productivity and Capacity review for Sept month requirements | Santosh S |  | ○
9 | 31.08.2017 | RV | Capacity improvement of Visco Assembly to meet 30000 Nos per month | Rajendra B |  | ○
10 | 31.08.2017 | RV | Enforcing FG scanning rule at each end of Line | Rajendra B / Gourav J |  | ○
11 | 31.08.2017 | RV | Enforcing Scanning of Heat exchanger at the end of Furnance - Explore scanning at Furnace Entry | Santosh S |  | ○
12 | 31.08.2017 | RV | VW Radiator Fin machine Productionize - Ensure all Systems are put in place | Abhay B |  | ○
○
14 | [5 empty] | ○
15 | [5 empty] | ○
16 | [5 empty] | ○
17 | [5 empty] | ○
18 | [5 empty] | ○
19 | [5 empty] | ○
20 | [5 empty] | ○
21 | [5 empty] | ○
22 | [5 empty] | ○
23 | [5 empty] | ○
24 | [5 empty] | ○
25 | [5 empty] | ○

## Open item list SFM level 3 Sept (hidden)
|  |  |  | Open Item List / Action Plan Sheet | [6 empty] | Status Legend:
[11 empty] | ○ | <25% umgesetzt
Subject: |  |  | Gap analysis |  |  |  |  | Date : |  | 2017-09-17 | ◔ | 25% umgesetzt
Editor: |  |  | Valmik Sangle | [7 empty] | ◑ | 50% umgesetzt
[6 empty] | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[11 empty] | ● | erledigt
Sr. No. | entered on: | Stn name | assigned by: | topic (Issue) | root cause (base for action) | to do / action | responsible: | due on: | status | comment:
1. | 2017-09-07 |  | Valmik S | Visco fan shortage (Y1031001) Repeted issue | Insert shortage @ supplier end |  | Ganesh/Milind |  | ○
|  |  | Valmik S | 1.P9218 pipe shortage 2. All heater pipe shortage (MY15,X104,P9218 &S106) | Capacity constraint @ supplier end (Yonoowoo) |  | Ganesh/Milind |  | ○
|  |  | Valmik S | Material shortage due to child part & separators containers to available | Containers & seperators maintenance not adhered (standard packing) | Issue need to taken with supplier & container maintenance (standard packing) | Ganesh/Milind |  | ○
2 | 2017-09-12 |  | Valmik S | Material delay from store HVAC- 551min Visco- | Plant visit preparation & casual reduce @ same time | In line process | Kashyap B | 2017-09-25 | ○
|  |  | Valmik S | Material Shortage HVAC- Duct & Wiring Visco- Fan | Duct BOM issue | Corrected BOM & arrange new material | Jagjivan/Rajendra B | 2017-09-12 | ●
|  |  |  | EP- GM tank, X over shroud | Delivery failure from supplier due to RM shortage & quality issue | Discuss with quality & purchase team | Ganesh | 2017-09-18 | ○
|  |  | Valmik S | CB1- Condensor PLC error & fin chute jam |  |  | Abhay B |  | ○
3 | 2017-09-13 |  | Valmik S | Material delay from store HVAC- 425min Visco- fna not found in store. | Fan Misplace | Monitoring in place for further action | Kashyap B | 2017-09-25 | ○
|  |  | Valmik S | (EGR) DLT loss time- models greaves & JCB | Fixture issue | DLT to be plan common for all modelswith working progress | Abhay B |  | ○
|  |  | Valmik S | CB2- Collector holder clamping problem | Clamping bolts are loose, alignment found disturb | Clamping bolts plan for modification with new design | Abhay B | 2017-09-17 | ○
4 | 2017-09-14 |  | Valmik S | Material delay & not found in store HVAC- 370min EC- Flat tube delay from aparna (180min) |  | Action lined up | Kashyap B |  | ○
|  |  | Valmik S | Material Shortage HVAC- S106 wiring EGR- 4SP & H6 diffuser shortage(240min) Cilynder shortage(110min) |  |  | Ganesh J |  | ○
|  |  | Valmik S | MFG HVAC- Hexa EOL not OK(425min) EGR- FAB. DLT prob(120min) |  |  | MFG |  | ○
|  |  |  | Maintenance Clinching railing bolt crack(VW) |  | All new bolt has been fitted at Machine | Abhay B |  | ●
6 | 2017-09-15 |  | Valmik S | Material Delay from store HVAC- Visco- |  |  | Kashyap B |  | ○
|  |  | Valmik S | Material Shortage HVAC- Battery cooling heater EP- Merlin tank |  |  | Ganesh J |  | ○
|  |  | Valmik S | EGR: LPT IIII Development parts production: Effective time loss | No fixtures for DLT & HLT, more false cycle |  | MFG |  | ○
7 | 2017-09-16 |  | Valmik S | Material Delay from store HVAC- 253min |  |  | Kashyap B |  | ○
|  |  | Valmik S | Material Shortage HVAC- Visco- Rust oil EC- Fiat manifold, M300 manifold |  |  | Ganesh J |  | ○
|  |  | Valmik S | HVAC- Hexa EOL LPC not working |  |  | Ramesh k/Amar P |  | ○
8 | 2017-09-18 |  | Valmik S | Material Delay from store HVAC- 350min Visco- 50min EP4- (R7822002,S3124001) | More time require to feed on line due to stack height | Additional stacker to be provided for long term sustainance (eRO is placed) | Kashyap B/Minild | 15/10/17 | ○
|  |  | Valmik S | Trolley shortage 1. HVAC- S106,P409 & CP bins 2. X-over motor shortage 3. X1 manifold shortage | 1. Customer dropping was not there 2. Planning issue 3. Capacity issue @ supplier end | 1. 15 trolley identified. 2. Planning tobe improved (immediate) 3. Capacity calculation to be done & initiate action. | Nakul/Kashyap B/Prashant J | 2017-10-10 | ○
|  |  | Valmik S | 1. Frame shortage due to furnace breakdown 2. Evap helium-2 cycle start issue & chamber evauation issue | Core stuck in conveyor | All posible causes tobe studied & identified.Action to be taken | Santosh/Abhay B | 22/09/17 | ○
9 | 2017-09-19 |  | Valmik S | Material delay from store HVAC- 230min Visco- 55min |  |  |  |  | ○
|  |  | Valmik S | Trolley shortage HVAC- vw,compact & Y1 |  |  |  |  | ○
|  |  | Valmik S | Evap & heater shortage Hexa S106 VW |  | Brazing need to be arranged & implemented for evaporators | Anand s / Santosh S |  | ○
10 | 2017-09-20 |  | Valmik S | Material Shortage HVAC- S106,man Visco- shaft U301 sealing,FF722001 (120min) LCCR motor |  |  |  |  | ○
|  |  | Valmik S | Material delay from store HVAC- S106,VW Compact (445min) Visco- 20min | Request flow is too high, unable to feed every material in time | High runner parts identified & relocate to bottom rack to reduce feeding time & delay. | Yogesh P | 19/10/2017 | ○
|  |  | Valmik S | X-over motor not clear from quality- R785001 (60min) CAC connector issue (120min) J92 unplanned setup as manifold was short during last setup (90min) |  |  |  |  | ○
11 | 2017-09-21 |  | Valmik S | Material shortage HVAC- Hexa, compact Visco- GY24001 fan |  |  | Malinath/ Milind M |  | ○
|  |  | Valmik S | EGR- Robot 3 Program modification lead time resulted in 300 min loss. |  |  | Sarang I/ Amol Patil |  | ○
12 | 2017-09-23 |  | Valmik S | Material Shortage EP- Painted condensor & DLE shroud EC- S101 manifold |  |  |  |  | ○
|  |  | Valmik S | Material delay from store M300- Fan & hose delay (120min) Fin delay from store (16487822- 60min) Tube delay- (44205001- 120min) |  |  |  |  | ○
|  |  | Valmik S | MP shortage EP3 & EP4 |  |  |  |  | ○
13 | 2017-09-25 |  | Valmik S | Heater & evap shortage from AH to HVAC lines. |  |  |  |  | ○
|  |  | Valmik S | EGR- P405 laser not ok |  |  |  |  | ○
14 | 2017-09-26 |  | Valmik S | Material delay from sstore HVAC- 213min |  |  |  |  | ○
|  |  | Valmik S | Material Shortage HVAC- 107min |  |  |  |  | ○
15 | 2017-09-28 |  | Valmik S | EGR- Laser is under breakdown since last night | M40 shulter issue |  |  |  | ○
|  |  | Valmik S | Material delay from store HVAC- 643min Visco- 75min |  |  |  |  | ○
|  |  | Valmik S | Material Shortage HVAC- 169min WIP shortage from nokolock to HVAC lines S106, VW, Compact, X104 | Heater pipe not found in store & shortage Fine leak in S106 (Bush Issue) |  |  |  | ○
16 | 2017-09-30 |  | Valmik S | Material delay from store HVAC- 260min
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34

## List Of Projects - Sep 2017 (hidden)
|  |  | Level 3 Meeting - List Of Projects |  |  |  |  | Status Legend:
[8 empty] | ○ | <25% umgesetzt
Subject: |  | CIP projects for the issues of Sept 2017 |  |  | Date : |  | 2017-09-02 | ◔ | 25% umgesetzt
Editor: |  | Valmik S | [5 empty] | ◑ | 50% umgesetzt
|  |  | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[8 empty] | ● | erledigt
Sr. No. | Entered on: | Assigned by: | Project Title | Responsible: | Due on: | Status | Comment:
1 | 2017-09-07 | Valmik S | Flow improvement to avoid Heater pipe shortage | Ganesh/Milind |  | ○
2 | 2017-09-07 | Valmik S | Standardization of containers for all child parts- Proper management ofr empty containers. | Ganesh/Milind |  | ○
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Open item list SFM level 3 Oct (hidden)
|  |  |  | Open Item List / Action Plan Sheet | [6 empty] | Status Legend:
[11 empty] | ○ | <25% umgesetzt
Subject: |  |  | Gap analysis |  |  |  |  | Date : |  | 2017-10-17 | ◔ | 25% umgesetzt
Editor: |  |  | Valmik Sangle | [7 empty] | ◑ | 50% umgesetzt
[6 empty] | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[11 empty] | ● | erledigt
Sr. No. | entered on: | Stn name | assigned by: | topic (Issue) | root cause (base for action) | to do / action | responsible: | due on: | status | comment:
1. | 2017-10-02 |  | Valmik S | Material Shortage HVAC- 562min Visco- 215min
|  |  | Valmik S | Material delay from store HVAC- 295min
|  |  | Valmik S | EGR- Laser cooling power issue | Pump Capacity
2 | 2017-10-03 |  | Valmik S | FG trolley & bin shortage HVAC- 531min (S106,EP,X104)
|  |  | Valmik S | Material Shortage HVAC- 516min Visco- 105min
|  |  | Valmik S | Material shortage from nokolok to HVAC line Hexa- Man-
3 | 2017-10-04 |  | Valmik S | Material Shortage HVAC- 500min Visco- 120min
|  |  | Valmik S | Material delay from store HVAC- 395min Visco- 70min
|  |  | Valmik S | Laser2- Welding not OK CB tube insertion problem
4 | 2017-10-05 |  | Valmik S | Material Shortage- HVAC- 867min Visco- 80min
|  |  | Valmik S | Material delay from store HVAC- 199min Visco- 25min
|  |  | Valmik S | Heater & evap shortage from AH to AG Hexa,VW,X104 & M&M
6 | 2017-10-06 |  | Valmik S | Material delay from store HVAC- 220min Visco- 90min
|  |  | Valmik S | Material Shortage- HVAC- VW,Verito,Y1 & VECV Visco- DD
|  |  | Valmik S | Heater & evap shortage from AH to AG Hexa,VW,X104 & M&M
7 | 2017-10-07 |  | Valmik S | Material Shortage HVAC- 780min | Delivery failure | Takeup with purchase & quality team to resolve | Ganesh J | 14/10/17 | ○
|  |  | Valmik S | Material delay from store HVAC- 246min Visco- 95min
8 | 2017-10-08 |  | Valmik S | Material delay from store HVAC- 80min Visco- 120min
|  |  | Valmik S | Material Shortage HVAC- 15min Visco- 20min | 1.Delivery failure from supplier due to raw material issue. 2. Filter inwarded @ wrong place. | 1. Discuss with top management & arrange. 2. Ensure in advance. | Ganesh J | 2017-12-10 | ○
|  |  | Valmik S | Evap shortage from AH line to HVAC line ( Hexa rear & M&M)
9 | 2017-10-10 |  | Valmik S | Material delay from store HVAC- 236min Visco- 75min
|  |  | Valmik S | Heater & evap shortage from AH to AG
|  |  | Valmik S | FG trolley shortage HVAC- X104, S106 & VW
10 | 25/11/2017 |  | Valmik S | Material Shortage- HVAC- 97min Visco- 230min
|  |  | Valmik S | Material delay from store- HVAC- 495min Visco- 230min
|  |  | Valmik S | EOL LPC not ok
11 | 26/11/2017 |  | Valmik S | Material Shortage- HVAC- 472min Visco- 225min
|  |  | Valmik S | Material delay from store- HVAC- 385min Visco- 75min
|  |  | Valmik S | Heater & evap shortage from AH to HVAC lines
12 | 28/11/2017 |  | Valmik S | Material Shortage- HVAC- 1080min Visco-
|  |  | Valmik S | Material delay from store- HVAC- 370min Visco- 125min
|  |  | Valmik S | Heater & evap shortage from AH to HVAC lines- 113min
13 | 29/11/2017 |  | Valmik S | Material Shortage- HVAC- 1080min Visco-
|  |  | Valmik S | Material delay from store- HVAC- 370min Visco- 125min
Valmik S
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34

## List Of Projects - OCT 2017 (hidden)
|  |  | Level 3 Meeting - List Of Projects |  |  |  |  | Status Legend:
[8 empty] | ○ | <25% umgesetzt
Subject: |  | CIP projects for the issues of Oct 2017 |  |  | Date : |  | 2017-10-02 | ◔ | 25% umgesetzt
Editor: |  | Valmik S | [5 empty] | ◑ | 50% umgesetzt
|  |  | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[8 empty] | ● | erledigt
Sr. No. | Entered on: | Assigned by: | Project Title | Responsible: | Due on: | Status | Comment:
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Open item list SFM level 3 Nov (hidden)
|  |  |  | Open Item List / Action Plan Sheet | [6 empty] | Status Legend:
[11 empty] | ○ | <25% umgesetzt
Subject: |  |  | Gap analysis |  |  |  |  | Date : |  | 2017-11-17 | ◔ | 25% umgesetzt
Editor: |  |  | R vasudevan | [7 empty] | ◑ | 50% umgesetzt
[6 empty] | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[11 empty] | ● | erledigt
Sr. No. | entered on: | Stn name | assigned by: | topic (Issue) | root cause (base for action) | to do / action | responsible: | due on: | status | comment:
1. | 2017-11-01 |  | Valmik S | Material Shortage- HVAC- 465min Visco- 25min
|  |  | Valmik S | FG trolley shortage- HVAC- 415min
|  |  | Valmik S | Material delay from store- HVAC- 393min Visco- 200min
2 | 2017-11-06 |  | Valmik S | FG trolley shortage- HVAC- 713min (S106,Man,CP & M&M) Visco- 15min (T80) | S106- No dropping Visco T80- No dropping Man- Excess overstock M&M- Delay due to traffic | Will plan & monitor | Santosh S & PPC | 17/11/17 | ○
|  |  | Valmik S | Material Shortage- HVAC- 420min Visco- 55min VW condensor shaper rod shortage |  |  |  |  | ○
|  |  | Valmik S | Material delay from store- HVAC- 205min Visco- 150min Radiator side support (U1675001) Condeser- CR3 breakdown | Request flow is high & 3 critical material in vehicle. CB motor shaft play. | Analysis req for flow data & kept high runner parts in bottom. | Yogesh P | 17/11/17 | ○
3 | 2017-11-07 |  | Valmik S | Air dispatch to delhi |  | Scheduling of parts 3days advance for delhi parts | Sunil K & Mallinath | 17/11/17 | ○
|  |  | Valmik S | Furnace- 1. Single furnace due to power supply issue. 2.Second furnace breakdown. 3. Condenser CB breakdown. 4. HVAC- 298min |  |  |  |  | ○
|  |  | Valmik S | Trolley Delay- Radiator- Merlin/FCA Condensor- Eagle HVAC- W105, CP & MAN | Both forklift breakdown For CP dock congection. | TO be done | Sunil K | 2017-08-11 | ○
|  |  | Valmik S | Material delay from store- HVAC- 360min Visco- 120min | Highest request flow | Need to add 1 more stacker | Yogesh P | 17/11/17 | ○
4 | 2017-11-08 |  | Valmik S | Material Shortage- HVAC- 130min Visco- 90min
|  |  | Valmik S | Evap & heater shortage to HVAC line
|  |  | Valmik S | Q- stop issue HVAC- 70min
6 | 2017-11-09 |  | Valmik S | Evap CB servo drive failed
|  |  | Valmik S | Material Shortage- HVAC- 210min Visco- 20min Collector shortage for VW/S101/MY15
|  |  | Valmik S | Q-issues- HVAC- vecv housing dim issue VW flap & housing matching issue X104 air flow issue
7 | 2017-11-11 |  | R Vasu | Material Shortage- HVAC- 245min Visco- 60min | Capacity issue @ supplier end | Providing sequence & qty for whole week by MBIPL to supplier to minimize setup & can be componsete with increased qty. | Vijay S/Ganesh J | 2017-11-13 | ○
|  |  | R Vasu | Material delay from store- HVAC- 147min | M&M line planned in 1st shift suddenly (80min downtime) Casual not available- 40min | 1. For unplanned line setup discuss with PPC & require to inform 16hrs before. 2. Take it with casual supervisor. | Yogesh P | 2017-11-11 | ●
|  |  | R Vasu | M/C: SPM P60- Diffuses welding & pipes welding | Servo motor of rotating fixture malfuction | Program correction tobe done for SPM | Amol P |  | ○
8 | 2017-11-13 |  | R Vasu | Material Shortage- HVAC- 542min Visco- 20min
|  |  | R Vasu | FG trolley shortage- HVAC- 105min (p405,x104,vw)
|  |  | R Vasu | Evaporator Shortage from AH to HVAC- 285min (S106,Y1,Hexa)
9 | 2017-11-14 |  | R Vasu | Material Shortage- HVAC- 570min Visco- 330min EC- Manifold shortage
10 | 2017-11-15 |  | R Vasu | Heater & evap shortage to HVAC line- 720min (Hexa,Battery cooling & VECV)
|  |  | R Vasu | Material Shortage- HVAC- 110min (FR446001 & B523586) Visco- EGR- GM317001,EV699001,FM294001,GG402001, Brazing core shortage.
|  |  | R Vasu | FG trolley shortage HVAC- 150min
|  |  | R Vasu | EGR m/c- R2 is under breakdown.
11 | 2017-11-16 |  | R Vasu | Material Shortage- HVAC- 200min EC- 40min(manifold)
|  |  | R Vasu | Visco- Oil checking m/c malfunctioning
12 | 2017-11-17 |  | R Vasu | Material Shortage- HVAC- 670min
|  |  | R Vasu | Material delay from store- HVAC- 181min Visco- 15min
|  |  | R Vasu | Heater & evap shortage to HVAC line
13 | 2017-11-18 |  | R Vasu | Material delay from store- HVAC- 159min Visco- 95min
|  |  | R Vasu | Heater & evap shortage to HVAC line (Hexa,Compact & VW)
|  |  | R Vasu | Material Shortage- HVAC- 70min EGR- Coiling 4sp material shortage.
|  |  | R Vasu | EGR- SPM one station is not working & welding not OK
14 | 2017-11-20 |  | R Vasu | FG trolley & FG box shortage. HVAC- 490min
|  |  | R Vasu | Heater & evap shortage to HVAC line- 395min
|  |  | R Vasu | Material Shortage- HVAC- 125min Visco- 30min
15 | 2017-11-22 |  | R Vasu | Material Shortage- HVAC- 199min Visco- 10min
|  |  | R Vasu | Material delay from store- HVAC- 150min Visco- 50min
|  |  | R Vasu | MFG- HVAC- Hexa EOL not OK for FATC model. Visco- Coil checking m/c not OK. (False cycle for distance)
16 | 2017-11-24 |  | R Vasu | Material Shortage- HVAC- 420min Visco- 20min
17 |  |  | R Vasu | Evap shortage from AH to HVAC- 365min
19 | 2017-11-25 | 2017-11-26 | R Vasu | Material Shortage- HVAC- 550min Visco- 30min
20 |  |  | R Vasu | Material delay from store- HVAC- 575min Visco- 65min
21 |  |  | R Vasu | Evap & heater shortage from AH to HVAC- 412min
22 | 2017-11-27 |  | R Vasu | Material Shortage- HVAC- 480min Visco- 200min
23 |  |  | R Vasu | Material delay from store- HVAC- 346min Visco- 35min
24 |  |  | R Vasu | FG trolley shortage HVAC- 426min
25 | 2017-11-28 |  | R Vasu | FG trolley shortage HVAC- 325min
26 |  |  | R Vasu | Material Shortage- HVAC- 83min Visco- 80min
27 |  |  | R Vasu | Heater & evap shortage from AH to HVAC- 301min
28 | 2017-11-29 |  | R Vasu | FG trolley shortage HVAC- 175min
29 |  |  | R Vasu | Material Shortage- HVAC- 70min Visco- 15min
31 | 2017-11-30 |  | R Vasu | Material Shortage- HVAC- 270min Visco- 70min
32 |  |  | R Vasu | Material delay from store- HVAC- 155min Visco- 115min
33 |  |  | R Vasu | Machine- HVAC- (X1 eol not ok 235min) Visco- (Coil checking m/c not ok)
34

## List Of Projects - NOV 2017 (hidden)
|  |  | Level 3 Meeting - List Of Projects |  |  |  |  | Status Legend:
[8 empty] | ○ | <25% umgesetzt
Subject: |  | CIP projects for the issues of Oct 2017 |  |  | Date : |  | 2017-11-02 | ◔ | 25% umgesetzt
Editor: |  | Valmik S | [5 empty] | ◑ | 50% umgesetzt
|  |  | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[8 empty] | ● | erledigt
Sr. No. | Entered on: | Assigned by: | Project Title | Responsible: | Due on: | Status | Comment:
1 | 2017-11-07 | RV | Condensor CB2 motor shaft play | Patil | 2017-11-07 | ● | Right side servomotor replaced with new
2 | 2017-11-09 | RV | M300 baffle leak | Sumit B | 2017-11-09 | ● | Baffle tilt
3 | 2017-11-10 | RV | Electric cable overhead cable project | Abhay B/ Yogesh B | 2017-11-10 | ◔
4 | 2017-11-10 | RV | Heijunka sequence broken | Kashyap | 2017-11-10 | ◑ | Sequence meeting tobe started
5 | 2017-11-10 | RV | Escalation procedure not follow during m/c breakdown | Yogesh B | 2017-11-12 | ● | Communication given to team member & procedure define
6 | 2017-11-10 | RV | Furnace maintenance | Abhay B/ Yogesh B | 2017-11-14 | ◑ | Workload planning
7 | 2017-11-10 | RV | Cond. CB3 capacity issue | Yogesh B | 2017-11-15 | ◕ | J92 cond. Tobe relocate from CB3 to semiauto CB
8 | 2017-11-07 | RV | Dispatch not not after loading | Sunil K | 2017-11-15 | ● | Prepare MIS for vehicle IN OUT & after loading
9 | 2017-11-08 | RV | Visco & EGR material avalaibility issue from Impression | Vijay | 2017-11-15 | ◑ | Share capacity for jan-18
10 | 2017-11-08 | RV | X104 trolley shortage | Sunil K | 2017-11-16 | ● | MP will be placed @ OEM plant
11 | 2017-11-10 | RV | Joint flux before trial & supply | Vijay S | 2017-11-17 | ● | Complete PPA with SFT & approve before SOP
12 | 2017-11-14 | RV | Material delay from store | Kashyap | 2017-11-17 | ● | Analysis data of req flow, high runner parts kept in bottom rack
13 | 2017-11-07 | RV | Customer coverage issue | Kashyap/CFT | 11/9/2017 10/11/2017 | ● | 1. Prepare plan to built 1 one stock for 5 measure (TML, M&M, VW, FCA Renult) 2. Plan to share the 1 DOH action
14 | 2017-11-18 | RV | Hexa hvac- front- mfg pt- st- PY for screw missing | Amol P | 2017-11-22 | ○ | Control panel, programming & interlocking with electric gum
15 | 2017-11-18 | RV | M&M hvac - TXV sensor forgot to remove in W105 | Amol P | 2017-11-22 | ○ | Need to update program
16 | 2017-11-18 | RV | Hexa- rear- AC- hvac-final rear assly-clamp/declamp | Amol P | 2017-11-22 | ○ | Need to add control panel, programming/electric gun
17 | 2017-11-17 | RV | EGR M/C uptime | Yogesh B | 2017-11-22 | ○ | Update about the availability of critical parts & skill
18 | 2017-11-17 | RV | Generation of picking list for SPD parts not available | Yogesh P | 2017-11-22 | ○ | Picking list concept to be followed for SPD parts as of OEM
19 | 2017-11-17 | RV | EGR SPM M/C process contrast | Amol P & Team | TBD | ○ | M/C has to rectify to suitable process
20 | 2017-11-18 | RV | New TXV assly station- Fixture for MY15 | Amol P & Team | 2017-12-10 | ○ | Procure new fixture for MY15,TXV + modify hardware to detect O-ring presence
21 | 2017-11-18 | RV | SMP 1 stage not working, welding not OK | Amol P & Team | TBD | ○
22 | 2017-11-18 | RV | Laser 2 -F3 alarm for 27 No. and 37 No.matrix | Amol P & Team | TBD | ○
23 | 2017-11-18 | RV | M300 CRFM-nut runner for motor/shroud /fan assly | Amol P & Team | 25/12/17 | ○ | Interlocking of fan assly station will declamp nut runner/Electrical nut runner
24 | 2017-11-18 | RV | New TXV assly station- O Ring , New camera sensored is required to be installed | Amol P | 25/12/17 | ◔ | Trial taken /order placed
24 | 2017-11-24 | RV | Hexa HVAC Blower balancing M/c RPM issue to impeller color | Anand.S |  |  | Possibilty of changening color of impeller
25 | 2017-11-24 | RV | Hexa HVAC Blower balancing M/c RPM issue due to impeller color | Amar.P |  |  | Implement the color sensor in M/c
26 | 2017-11-22 | RV | Visco m/c 3 abnormal noise due to torque sensor allignment issue m/c | Karmarkar |  |  | Need to do proper allingment for torque sensor implementation
27 | 2017-11-22 | RV | L200 part (X104 & X1 defrost lever Shift angle) | Vikas.A | 2017-11-24 |  | Freeze the drawing with updated angle
28 | 2017-11-23 | RV | False cycle in Visco coil checking M/c | Raemsh K |  |  | Set Revised parameters in CP & M/c
29

## Open item list SFM level 3 Dec (hidden)
|  |  |  | Open Item List / Action Plan Sheet | [6 empty] | Status Legend:
[11 empty] | ○ | <25% umgesetzt
Subject: |  |  | Gap analysis |  |  |  |  | Date : |  | 2017-12-17 | ◔ | 25% umgesetzt
Editor: |  |  | R vasudevan | [7 empty] | ◑ | 50% umgesetzt
[6 empty] | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[11 empty] | ● | erledigt
Sr. No. | entered on: | Stn name | assigned by: | topic (Issue) | root cause (base for action) | to do / action | responsible: | due on: | status | comment:
1. | 2017-12-02 |  | R Vasu | Material delay from store- HVAC- 460min Visco- 30min
|  |  | R Vasu | FG trolley shortage- HVAC- 160min
|  |  | R Vasu | X1 EOL- Air flow parameter need to freezed. Visco coil checking- False cycle
2 | 2017-12-04 |  | R Vasu | FG trolley shortage- HVAC- 350min
|  |  | R Vasu | Machine- EOL not OK- vw,x1(125min) Visco- Oil feelig m/c job sensor not ok. Coil checking m/c false cycle issue.
|  |  | R Vasu | Visco- Test m/c 5 under fine tuning TLC evisco produced 114 against schedule of 360 in same m/c
3 | 2017-12-05 |  | R Vasu | FG trolley shortage- HVAC- 590min (Hexa,S106 & Compact)
|  |  | R Vasu | Material delay from store- HVAC- 150min Visco- 45min
|  |  | R Vasu | Machine Issues- Visco- coil cycle m/c false cycle HVAC- Kinematic pressring m/c bracket fitment issue.
4 | 2017-12-07 |  | R Vasu | Material Shortage- HVAC- 356min Visco- 30min
|  |  | R Vasu | FG trolley shortage- HVAC- 155min
|  |  | R Vasu | Machine issues- 1. HVAC- Eol not ok (X1 & Compact) 2. Visco- Testing m/c 5 still under MFG for program modification.
5 | 2017-12-09 |  | R Vasu | Machine issue- 1. X1/X104 EOL airflow not ok (HVAC) 2. Visco- Coil checking m/c false cycle issues.
|  |  | R Vasu | Material Shortage- HVAC- 70min Visco- 40min
|  |  | R Vasu | Heater & Evap shortage from AH to HVAC lines- 140min
6 | 2017-12-11 |  | R Vasu | Material Shortage- HVAC- 165min Visco- 15min
|  |  | R Vasu | Material delay from store- HVAC- 123min Visco- 40min
|  |  | R Vasu | Material issues- 1. X104 manual model airflow not ok (HVAC) 2. Hall sensor not ok in coil checking m/c (Visco)
7 | 2017-12-12 |  | R Vasu | Material Shortage- HVAC- 317min Visco-
|  |  | R Vasu | Machine Issue- HVAC- Airflow not OK issue in EOL (X104) Visco- Coil checking hole sensor not ok. Heater- Fin cutting issue.
|  |  | R Vasu | FG trolley & packing mtl issue. HVAC- 60min Visco- 70min
8 | 2017-12-14 |  | R Vasu | Machine Issue- HVAC- Airflow not OK issue in EOL (X104) Visco- Coil checking hole sensor not ok. Heater- Fin cutting issue.
|  |  | R Vasu | Quality Issue HVAC- Contact element dimension not OK.
|  |  | R Vasu | Evap Shortage- Verito- 420min
9 | 2017-12-17 |  | R Vasu | Material Shortage- HVAC- 233min Visco- 20min
|  |  | R Vasu | Material delay from store- HVAC- 30min Visco- 75min
|  |  | R Vasu | Machine Issue- HVAC- Airflow not OK issue in EOL (X104) Visco- Coil checking hole sensor not ok.
9 | 2017-12-18 |  | R Vasu | Material Shortage- HVAC- 95min Visco- 340min
|  |  | R Vasu | Quality Issue HVAC- Contact element dimension not OK.
|  |  | R Vasu | Machine Issue- HVAC- Airflow not OK issue in EOL (X104) Visco- M/c 5 under MFG for program modification.
10 | 2017-12-20 |  | R Vasu | Q issues- HVAC- 158min VW evap & f/r housing extra mtl.
|  |  | R Vasu | Machine Issue- Visco- Coil checking hole sensor not ok. Test m/c-2 tube temp not ok. Test m/c-3 resistance not ok.
|  |  | R Vasu | Heater & Evap shortage for Hexa & Battery cooling from AH to HVAC- 90min.
| 2017-12-21 | 2017-12-22 | R Vasu | Q- Issues HVAC wrong hsg from supplier Contact element dimension issues
|  |  | R Vasu | FG box (VECV) & FG trolley shortage. (X104)
|  |  | R Vasu | Material delay from store. HVAC- 60min
12 | 2017-12-23 |  | R Vasu | Material Shortage- HVAC- 388min
|  |  | R Vasu | Material delay from store. HVAC- 85min Visco- 85min
|  |  | R Vasu | Q issues- 1. HVAC- X104 airflow not okin EOL. 2. Lever L2000 cavity issue. 3. M/c parameter not ok.
13 | 2017-12-30 |  | R Vasu | Material Shortage- Visco- L6763 cover & X7305001 fan. | Plan increased from 80 to 230nos. | Discuss with PPC & resolve |  | 2017-12-30 | ●
|  |  | R Vasu | Machine Issues- Visco- E-visco wiring station crimming tool damage (alligment not OK)
R Vasu
14
15
16
17
19
20
21
22
23
24
25
26
27
28
29
31
32
33
34

## List Of Projects - Dec 2017 (hidden)
|  |  | Level 3 Meeting - List Of Projects | [6 empty] | Status Legend:
[10 empty] | ○ | <25% umgesetzt
Subject: |  |  | CIP projects for the Dec 2017 |  |  |  | Date : |  | 2017-12-02 | ◔ | 25% umgesetzt
Editor: | [9 empty] | ◑ | 50% umgesetzt
|  |  |  | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed | [5 empty] | ◕ | 75% umgesetzt
[10 empty] | ● | erledigt
Sr. No. | Entered on: | Dept | Assigned by: | Project Title | Action Taken | Responsible: | Due on: | Status | Comment:
1 | 2017-05-12 | Quality |  | HVAC damage Mahindra nashik (No dock audit persons in night shift) |  | Babu M |  | ○
2 | 2017-12-12 | Quality |  | Wrong VW gasket came on line | Block gasket in system | Babu M | 15/12/2017 | ○
3 | 13/12/2017 | Design | Vithal | Contact element- W105 CP | Drawing to be updated for tolerance | V. Mohindikar | 18/12/2017 | ○
4 | 14/12/2017 | Logistic | Sunil K | Attending level- 2 meeting by by dispatch with trolley details format updated |  | Sunil K |  | ○
5 | 2017-07-12 | MFG | Amol P | Visco line tooling & equipment spare drawing not available & m/c getting down due to same. | Need to provide all approved drawing | Amol P |  | ○
6 | 2017-07-12 | Prod | Santosh S | Hexa evap torque gun 3.5KN spare not available (electric) | Spare gun need tobe provided | Amar P |  | ○
7 | 2017-05-12 | Prod | Santosh S | Parts mixed up & damage for HHA evap ( against 240 nos- 30 nos H79) | Scanning of half qty will be done immediately | Santosh S |  | ○
8 | 24/12/2017 | Quality |  | Hexa hvac blower balancing m/c RPM issue due to impeller transperant with deviation | ICA coloring of impeller edge by blue colour paint marker | Rajendra B | 24/12/2017 | ○
9 | 13/12/17 | MFG | RV | EGR old core builder electrical drawing and PLC programe backup not available | Need to provide all backup | Amol P
10 |  | Tooling | RV | Cutting problem in Evap Fin M/c |  | Yogesh.B
11 | 2017-06-12 |  | RV | Material delay from store (All products core) | Teporary action f/Completion of permanent action of taking material from upper layer to middle layer | Yogesh .P | 28/12/17
12 |  | MFG | RV | EGR SPM M/c process constraint | M/c has to rectify suitable process | Amol.P
|  |  | RV | X104 Trolley shortage | 40 Trolley to be added urgently | Sunil.K | 2018-07-01
14 |  | HR | RV | Manpower shortage for packaging | Need to ensure manpower as per requirement | Pankaj
15
16
17
18
19
20
21
22
23
24
25

## Open item list SFM level 3 (2) (hidden)
|  |  |  | Open Item List / Action Plan Sheet | [6 empty] | Status Legend:
[11 empty] | ○ | <25% umgesetzt
Subject: |  |  | Gap analysis |  |  |  |  | Date : |  | 2017-12-17 | ◔ | 25% umgesetzt
Editor: |  |  | R vasudevan | [7 empty] | ◑ | 50% umgesetzt
[6 empty] | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed |  |  |  |  | ◕ | 75% umgesetzt
[11 empty] | ● | erledigt
Sr. No. | entered on: | Stn name | assigned by: | topic (Issue) | root cause (base for action) | to do / action | responsible: | due on: | status | comment:
1. | 2017-12-02 |  | R Vasu | Material delay from store- HVAC- 460min Visco- 30min
|  |  | R Vasu | FG trolley shortage- HVAC- 160min
|  |  | R Vasu | X1 EOL- Air flow parameter need to freezed. Visco coil checking- False cycle
2 | 2017-12-04 |  | R Vasu | FG trolley shortage- HVAC- 350min
|  |  | R Vasu | Machine- EOL not OK- vw,x1(125min) Visco- Oil feelig m/c job sensor not ok. Coil checking m/c false cycle issue.
|  |  | R Vasu | Visco- Test m/c 5 under fine tuning TLC evisco produced 114 against schedule of 360 in same m/c
3 | 2017-12-05 |  | R Vasu | FG trolley shortage- HVAC- 590min (Hexa,S106 & Compact)
|  |  | R Vasu | Material delay from store- HVAC- 150min Visco- 45min
|  |  | R Vasu | Machine Issues- Visco- coil cycle m/c false cycle HVAC- Kinematic pressring m/c bracket fitment issue.
4 | 2017-12-07 |  | R Vasu | Material Shortage- HVAC- 356min Visco- 30min
|  |  | R Vasu | FG trolley shortage- HVAC- 155min
|  |  | R Vasu | Machine issues- 1. HVAC- Eol not ok (X1 & Compact) 2. Visco- Testing m/c 5 still under MFG for program modification.
5 | 2017-12-09 |  | R Vasu | Machine issue- 1. X1/X104 EOL airflow not ok (HVAC) 2. Visco- Coil checking m/c false cycle issues.
|  |  | R Vasu | Material Shortage- HVAC- 70min Visco- 40min
|  |  | R Vasu | Heater & Evap shortage from AH to HVAC lines- 140min
6 | 2017-12-11 |  | R Vasu | Material Shortage- HVAC- 165min Visco- 15min
|  |  | R Vasu | Material delay from store- HVAC- 123min Visco- 40min
|  |  | R Vasu | Material issues- 1. X104 manual model airflow not ok (HVAC) 2. Hall sensor not ok in coil checking m/c (Visco)
7 | 2017-12-12 |  | R Vasu | Material Shortage- HVAC- 317min Visco-
|  |  | R Vasu | Machine Issue- HVAC- Airflow not OK issue in EOL (X104) Visco- Coil checking hole sensor not ok. Heater- Fin cutting issue.
|  |  | R Vasu | FG trolley & packing mtl issue. HVAC- 60min Visco- 70min
8 | 2017-12-14 |  | R Vasu | Machine Issue- HVAC- Airflow not OK issue in EOL (X104) Visco- Coil checking hole sensor not ok. Heater- Fin cutting issue.
|  |  | R Vasu | Quality Issue HVAC- Contact element dimension not OK.
|  |  | R Vasu | Evap Shortage- Verito- 420min
9 | 2017-12-17 |  | R Vasu | Material Shortage- HVAC- 233min Visco- 20min
|  |  | R Vasu | Material delay from store- HVAC- 30min Visco- 75min
|  |  | R Vasu | Machine Issue- HVAC- Airflow not OK issue in EOL (X104) Visco- Coil checking hole sensor not ok.
9 | 2017-12-18 |  | R Vasu | Material Shortage- HVAC- 95min Visco- 340min
|  |  | R Vasu | Quality Issue HVAC- Contact element dimension not OK.
|  |  | R Vasu | Machine Issue- HVAC- Airflow not OK issue in EOL (X104) Visco- M/c 5 under MFG for program modification.
10 | 2017-12-20 |  | R Vasu | Q issues- HVAC- 158min VW evap & f/r housing extra mtl.
|  |  | R Vasu | Machine Issue- Visco- Coil checking hole sensor not ok. Test m/c-2 tube temp not ok. Test m/c-3 resistance not ok.
|  |  | R Vasu | Heater & Evap shortage for Hexa & Battery cooling from AH to HVAC- 90min.
| 2017-12-21 | 2017-12-22 | R Vasu | Q- Issues HVAC wrong hsg from supplier Contact element dimension issues
|  |  | R Vasu | FG box (VECV) & FG trolley shortage. (X104)
|  |  | R Vasu | Material delay from store. HVAC- 60min
12 | 2017-12-23 |  | R Vasu | Material Shortage- HVAC- 388min
|  |  | R Vasu | Material delay from store. HVAC- 85min Visco- 85min
|  |  | R Vasu | Q issues- 1. HVAC- X104 airflow not okin EOL. 2. Lever L2000 cavity issue. 3. M/c parameter not ok.
13 | 2017-12-30 |  | R Vasu | Material Shortage- Visco- L6763 cover & X7305001 fan. | Plan increased from 80 to 230nos. | Discuss with PPC & resolve |  | 2017-12-30 | ●
|  |  | R Vasu | Machine Issues- Visco- E-visco wiring station crimming tool damage (alligment not OK)
R Vasu
14
15
16
17
19
20
21
22
23
24
25
26
27
28
29
31
32
33
34

## Product Development
|  | Workwear Segment Open Points | [7 empty] | Status Legend:
[10 empty] | ○ | <25% umgesetzt
Subject: |  | Workwear projects |  |  |  |  | Date : |  | 2021-06-01 | ◔ | 25% umgesetzt
Editor: |  | Fahad Kazi | [7 empty] | ◑ | 50% umgesetzt
|  |  | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed | [6 empty] | ◕ | 75% umgesetzt
[10 empty] | ● | erledigt
Sr. No. | Entered on: | Type | Project Title | What to do? | Action Taken | Responsible: | Due on: | Status | Comment:
1 | 2021-06-25 | Product Design | Catalogue designing - For Industrial, Healthcare |  | First Copy is complete. Needs Improvement | Fahad Kazi |  | ◕ | Design sketches needs to be updated. CIP
2 | 2021-06-25 | Product Design | Design sketches | 50-60 design sketches have to be created | 25-30 designs have been created at this stage. | Fahad Kazi | 2021-07-03 | ◕
3 | 2021-06-25 | Product Design | Fashion Designer | Need a fashion designer for design sketches |  | Fahad Kazi |  | ○ | Not required at this stage
4 | 2021-06-25 | Material Procurement | Product samples for healthcare, cotton & FR |  | Have procured samples from Multiple sources such as Redstar, Karam, Sure Safety, etc. Still more samples to be procured for shirts, pants, etc | Irfan Chikte, Fahad Kazi | 2021-07-03 | ◕ | More samples to be procured from Redstar for Denim wear, shirts, Pants
5 | 2021-06-25 | Material Procurement | Fabric Patch Samples - Pure cotton, FR, etc |  | 1. Pure cotton patch samples are arranged from local, branded mills. 2. FR Patch samples are arranged from Arvind, Coats, etc | Irfan Chikte, Fahad Kazi | 2021-07-10 | ◕ | More patch samples to be arranged for Teijin and other speciliased fabrics such as Oil resistant, water resistant, etc
6 | 2021-06-25 | Material Procurement | Fabric sample for design studio | 20 Meter samples for each color and weight has to be arranged in 100% cotton fabric for design samples | Needs to be done | Irfan Chikte, Fahad Kazi | 2021-07-10 | ○ | Can be arranged through local fabric dealers in Mangaldas market or Dadar region
7 | 2021-06-25 | Material Procurement | Identifying fabric mfr’s as per Industry standards | Need to identify fabric manufacturers | 1. For FR requirement, Arvind mill, Madura coats, Teijin Aramid have been identified. 2. For Premium FR range, Marina Textil has been identified | Irfan Chikte, Fahad Kazi |  | ◑ | Need to identify more fabric mfr's for specialised fabrics such as oil resistant, chemical resistant, etc
8 | 2021-06-25 | Material Procurement | Identifying sources for Zipper | Regular and FR Zippers have to be sourced (YKK) | YKK regular brass zipper are identified | Irfan Chikte, Fahad Kazi |  | ◑ | Need to check for FR Zippers
9 | 2021-06-25 | Material Procurement | Identifying sources for Buttons | Buttons have to be sourced |  | Irfan Chikte, Fahad Kazi |  | ○ | Need to find good source for brass buttons
10 | 2021-06-25 | Material Procurement | Identifying sources for Thread | Regular and FR Thread have to be sourced |  | Irfan Chikte, Fahad Kazi |  | ○ | Need to find good source for regular and FR threads
11 | 2021-06-25 | Material Procurement | Identifying sources for Reflective tape | Regular and FR Reflective tapes have to be sourced (3M or equivalent) | 3M FR reflective tapes are identified | Irfan Chikte, Fahad Kazi |  | ◑ | Need to find good source for regular reflective tapes
12 | 2021-06-25 | Product Development | Tailor Master | Need a tailor master for sample generation |  | Irfan Chikte, Fahad Kazi | 2021-07-10 | ○ | Need to find out at the earliest
13 | 2021-06-25 | Product Development | Sample Generation | Need to create 5-6 samples for each design, color and weight |  | Irfan Chikte, Fahad Kazi |  | ○ | Needs to be done at the earliest
14 | 2021-06-25 | Product Development | Packaging and label development | Packaging and labelling has to be improved to match the market | Primary packaging and labelling is generated. Needs improvement | Irfan Chikte, Fahad Kazi |  | ◑
15 | 2021-06-25 | Testing and Certification | FR garments testing and Certification | 1. Need to get it tested from Indian govt. labs like BTRA, ATIRA, etc 2. Need to get it tested from SGS, BV | Proban, Protex coverall have been tested for NFPA 2112 | Fahad Kazi |  | ◔ | 1. Other products have to be tested for NFPA 2112 from BTRA. 2. Need to test for EN 11611, EN 11612, EN 1149 from ATIRA 3. Need to be tested from SGS or BV.
16 | 2021-06-25 | Testing and Certification | Healthcare garments testing and Certification | 1. Certfy to ASTM F 1670 / F 1670M-08 / ISO 16603 class 3 & ISO 22612:2005 2. FDA and CE approval | ASTM F 1670 / F 1670M-08 / ISO 16603 class 3 & ISO 22612:2005 Approved | Irfan Chikte, Fahad Kazi |  | ◑ | FDA and CE needs to be approved
17 | 2021-06-25 | Brand name and trademark | Brand name and trademark registry | 1. Need to finalise brand name for Industrial and Healthcare workwear 2. Need to register the trademark |  | Irfan Chikte, Fahad Kazi | 2021-07-10 | ○ | Need to do it on Priority

## Business Development
|  | Workwear Open Points | [7 empty] | Status Legend:
[10 empty] | ○ | <25% umgesetzt
Subject: |  | Workwear projects |  |  |  |  | Date : |  | 2021-06-01 | ◔ | 25% umgesetzt
Editor: |  | Fahad Kazi | [7 empty] | ◑ | 50% umgesetzt
|  |  | Legend: ○< 25% done; ◔ 25% done; ◑ 50% done; ◕ 75% done; ● completed | [6 empty] | ◕ | 75% umgesetzt
[10 empty] | ● | erledigt
Sr. No. | Entered on: | Type | Project Title | What to do? | Action Taken | Responsible: | Due on: | Status | Comment:
1 | 2021-06-25 | Business Development | PPT offering for MENA region ( Middle East) |  | Completed | Irfan Chikte |  | ●
2 | 2021-06-25 | Business Development | PPT offering for MENA region ( India) |  | Completed | Irfan Chikte |  | ●
3 | 2021-06-25 | Business Development | E commerce website |  | Completed | Irfan Chikte, Fahad Kazi |  | ●
4 | 2021-06-25 | Business Development | Appointing a sales team | Need to appoint a sales person who has good Industrial sales background |  | Irfan Chikte | 2021-07-10 | ○ | Need to check on Priority
5 | 2021-06-25 | Business Development | Appointing sub-distributors | Need to appoint sub-distributors |  |  |  | ○ | Need to check on Priority
6 | 2021-06-25 | Business Development | Social Media marketing | 1. Need to identify relevant clients on social media and follow, connect with them 2. Try to get their contact detials to directly reach out to them 3. Increase the post frequency to 3-4 posts/week | CIP | Fahad Kazi |  | ◔ | CIP
7 | 2021-06-25 | Business Development | Identify segments and potential clients | Try to get potential client details and reach out to them through calls, emails, linkedin, etc | CIP | Fahad Kazi, Irfan Chikte |  | ○ | CIP
8 | 2021-06-25 | Business Development | Registered customers for requirement | Introduce our new segment to previous customers | CIP | Fahad Kazi, Irfan Chikte |  | ○ | CIP
9 | 2021-06-25 | Business Development | Identify export leads | Need to identify export safety traders | CIP | Fahad Kazi, Irfan Chikte |  | ○ | CIP
10 | 2021-06-25 | Business Development | Govt. and Private Tenders | Keep a track of tenders on e procure and bid for it regularly | CIP | Fahad Kazi, Irfan Chikte |  | ○ | CIP
11 | 2021-06-25 | Business Development | Product listings on GEM | List the products on GEM and bid for workwear tenders |  | Fahad Kazi |  | ○ | Testing is awaited
12 | 2021-06-25 | Business Development | Indiamart leads | Keep a track of leads on Indiamart and quote for it | CIP | Fahad Kazi |  | ○ | CIP